## Slide 1: Supportive Services for Veteran Families (SSVF) Webinar Series: Program Start-Up for New Grantees
August 12, 2013

## Slide 2: Agenda for This Webinar
Overview: Organizing the Work
Your Agreement with VA: Grant Administration and Program Compliance Checklist
Your Program Design and Implementation: New Grantee Program Start-up Checklist
HMIS: HMIS Checklist & Discussion Guide for New SSVF Grantees
Questions?

## Slide 3: Presenters
Linda Southcott, SSVF Program Office
Jeffrey Houser, SSVF Program Office
Jeffrey Ward, Abt Associates
Marge Wherley, Abt Associates

## Slide 4: Overview: Organizing the Work
Your overarching goals:
Timely start-up: delivering services a.s.a.p.
Compliance with VA regulations, rules and agreement requirements
Internal program consistency: making sure the pieces fit together and that each reinforces the three core concepts:
Housing First philosophy
Crisis Response intervention
Client Choice

## Slide 5: Timely Start-Up
Develop a master timeline, incorporating the tasks included on the checklists. Tip: May need mini-timelines; many tasks require multiple actions.
Identify priorities, assign task responsibilities to specific staff, set due dates, and assure appropriate review. Tip: MOA finalization, fiscal set-up, staff hiring steps, and training regarding VA requirements are the highest priority. Carefully consider both time constraints and expertise requirements when assigning a task or timeline to a group vs. an individual.

## Slide 6: Compliance
Review requirements (statutes, rules, NOFA, the terms of your agreement with VA). Tip: Assign homework to all appropriate staff, utilizing resources posted on VA’s SSVF Grantee Website. You may want to consider testing staff understanding via case scenarios, etc.
Translate requirements into policies—then determine the procedures (processes, staff roles, timelines) necessary to implement policies. Tip: As you develop procedures and make decisions about who is responsible for each, you may revise job descriptions and/or your training plan. This task is iterative: you will continue to revisit these when requirements change and as program experience suggests better processes.

## Slide 7: Internal Consistency
All program components should be mutually reinforcing. Tip: When assigning different components to different staff, be sure to assign an individual or committee to review all components for inconsistencies, gaps, etc.
Ask yourself whether each of the pieces (staffing, processes, forms, etc.) reinforces the core concepts and best practices. Tip: Assign homework—all staff should review Webinars (Housing First, Progressive Case Management, Fidelity Standards) and SSVF Program Standards on VA’s SSVF Grantee Website.
Assure that administrative and programmatic decisions are not made in separate “silos.” Tip: Provide overview of program to administrative and fiscal staff; provide overview of administrative/fiscal roles/processes to program staff. Assure some method of cross-representation as program is designed and implemented.

## Slide 8: VA Grant Administration and Program Compliance Checklist
Linda Southcott, VA Program Office
Jeffrey Houser, VA Program office

## Slide 9: Payment Management System
Goals:
Set up account
Establish direct deposit for federal SSVF funds
Set up subaccounts in accordance with VA reporting requirements
Know the process to make draws
Draw from any/all accounts (approval within 24 hours)

## Slide 10: Grant Agreement and Application (Pre-Agreement Meeting)
VA will contact Grantees to schedule pre-agreement meeting
Meeting topics will include:
  Eligible activities/services
  Targeted subpopulations
  Geographic areas served / CoC
  Community Type
  Subcontractors, Management/MOAs
  HMIS Administration
  Approved Budget:
    Eligible Expenses per Category
    Quarterly Projections
    Subcontractor Expenses

## Slide 11: Fiscal Compliance
Grantees must know and assure their financial systems and processes comply with all applicable requirements, including:
Financial Services Center—Audit Selections
OMB Circular A122
OMB Circular A133
Close-Out Certifications
Single Audit Submissions

## Slide 12: Reporting Requirements
Set up infrastructure/software, timelines, procedures, training and staff responsibilities for:
Qualitative Reports: Quarterly Report (PDF); Participant Surveys; Critical Incident
Financial Reports: Quarterly Report Attachment 1 (Excel)
Quantitative Reports: HMIS (ongoing); VA Repository Uploads (monthly); Coversheet Submission (Excel) or Non-HMIS Data (monthly)

## Slide 13: Program Operations
Know the processes for:
Communication with VA. Use of Regional Coordinators; SSVF General Inbox (ssvf@va.gov); Grantee Identification/Grant Award Number
Making Program Changes: “Significant” changes; Budget Modifications; Sub-account Funds Transfers

## Slide 14: Program Operations (cont.)
Know the processes for:
Program Remediation: Corrective Action Plans; Management Improvement Plans
Training and Technical Assistance: SSVF Program Guide; Website: Grantee Resources/Knowledge University; National Webinars; Regional Coordinator Live Meetings; Individual Technical Assistance (as needed)

## Slide 15: New Grantee Program Start-up Checklist
Marge Wherley, Abt Associates

## Slide 16: Overall….
Completing all the tasks will require a lot of work!
There is a real tension between the timely implementation of program services and the infrastructure needed to assure compliance and internal program consistency.
You will have to build the plane while you are flying it, which will cause anxiety and frustration for many staff.
Realize that this is not work that you can do once: modifications will be possible/necessary (that’s the good news AND the bad).

## Slide 17: Hire/Designate Staff
Carefully consider what each position is designed to accomplish and the best experience and/or training needed to do that effectively.
Consider veterans and people who were formerly homeless: rich experience and possibly special needs for training/supervision.
Assure that potential SSVF staff can promote the core concepts of SSVF.

## Slide 18: Train Staff
Staff must be able to see the forest, the trees and (sometimes) the leaves:
Veteran homelessness as a national issue
Rapid Re-Housing and Homelessness Prevention as national models
The VA’s SSVF program--mission, core concepts, standards and best practices, temporary financial assistance, case management, etc.
Program requirements: Eligibility, screening, assessment, housing plans, policies and procedures, job duties, forms, data collection, etc.
Community resources for SSVF program participants: housing, income enhancement, etc.

## Slide 19: Develop Policies and Procedures (and Forms)
Start with VA requirements (statutory, rules, NOFA, agreement): these become mandatory policies
Develop additional policies as needed to implement your specific SSVF program (must not conflict with VA requirements)
Procedures are the steps and processes to carry out policy: which staff, what tasks, how often, how documented/reviewed.
This assures a focused approach and avoids loss of program integrity when staff turnover occurs.

## Slide 20: Outreach and Referral
Tailor outreach materials, methods, and partnerships to the specific population(s) and location(s) you serve.
Emphasize connections with the community resources and the locations where you will find people experiencing homelessness
Assure your prevention screening tool and your intake process will result in rapidly assisting households most likely to become homeless.

## Slide 21: Service Referral and Coordination
Identify key sources of referrals to your program and resources that will accept referrals from your program. Develop protocols for referrals/coordination:
VA resources: Medical Center(s), VA Community Resource and Referral center(s), GPD, VASH, HVRP, etc.
Other SSVF grantees
CoC representatives/members
Other resources: mainstream employment, public benefits, non-traditional resources, etc.

## Slide 22: Housing Referral and Coordination
Housing providers /landlords are extremely critical partners.
Develop relationships with all subsidized housing resources: know eligibility, application, waiting lists, etc.
Recruit and retain private market landlords through landlord and tenant supports/incentives

## Slide 23: Financial Assistance Administration
Policies and procedures governing your financial assistance/rental assistance should assure that assistance is at the lowest level necessary for the shortest period of time necessary to resolve the housing crisis.
Develop the processes and documentation requirements for staff to calculate and request financial assistance, review/approval and issuing payments (to a third party)

## Slide 24: Subcontractors (if applicable)
Develop and execute subcontractor agreements
Establish subcontractor invoice and payment policies, procedures, forms
Train subcontractors on policies, procedures, forms, etc.
Require subcontractors to develop specific policies and procedures necessary to implement subcontracted services.
Establish a subcontractor monitoring plan

## Slide 25: HMIS Checklist and Discussion Guide for New SSVF Grantees
Jeff Ward, Abt Associates

## Slide 26: Overall….
Participation in HMIS is required and the data you collect is critical to your program and to the SSVF program.
SSVF is a demanding HMIS application. But SSVF Grantees have been remarkably successful in completing accurate, on time uploads to the VA Repository. You will be successful, too.
Many steps in the checklist must occur in sequence and some have significant lead times. Start today.
Do not hesitate to ask for help. Your SSVF Regional Coordinator is your connection to TA

## Slide 27: Step 1: Learn About HMIS
Review HMIS Data Standards to understand HMIS requirements for data collection
Review 2004 HMIS Data and Technical Standards to understand security and privacy standards for HMIS
Check OneCPD Resource Exchange page for updates on HMIS. On this site, subscribe to receive HUD email updates on HMIS

## Slide 28: Step 2: Initiate contact with your HMIS lead and CoC Chairperson
Learn about your CoC(s) HMIS Implementation: locally defined participation requirements, software provider, participation costs, agreements, local data collection/privacy/security/data quality requirements beyond federal requirements.
Communicate your SSVF reporting needs to the HMIS lead agency(ies), including monthly export and upload requirements and SSVF-specific data elements. See SSVF Data Collection Guidance.

## Slide 29: Step 3: HMIS Enrollment
Negotiate and execute agreements such as agency participation agreement, end user agreement, business associate agreement, subcontractor agreement.
Establish data sharing policy for SSVF client data: what data will be shared and with whom?
Set training timeline with administrator: administrator provides training on data collection, privacy and security, reporting

## Slide 30: Step 4: Implementing HMIS within your SSVF Program
Organize for data collect: Establish data collection structure, draft workflow and data collection procedures, develop data collection forms, select and train data entry staff and obtain individual logons and passwords.
Manage data collection: Establish management accountability for data collection. Review data collection for completeness and accuracy daily. Use HMIS reporting to highlight missing data at least weekly.
Apply corrective action early: Provide additional training, revise input forms, change workflow, consider staffing changes as necessary.

## Slide 31: Step 5: Creating and Monitoring Data Quality Standards
Develop data quality plan in conjunction with CoC(s). See “Developing an Excellent Data Quality Plan” Webinar posted on SSVF Grantee website.
Include regular, high level monitoring of data collection and the entry process to assure timeliness, completeness, accuracy. Feedback to managers and staff as needed.

## Slide 32: Step 6: Upload Your data to the VA’s Repository
Preparation for the upload: Confirm that all information for the calendar month has been entered into HMIS. Check for missing or erroneous data. Generate a standard XML or CSV export from the HMIS system.
Upload to the VA Repository: Log onto the VA Repository website and upload the export file as early as possible. Data can be entered (or reentered) any time between the first and fifth business day of each month. If the upload is rejected, correct errors noted and resubmit data into repository.

## Slide 33: Summarizing

## Slide 34: Tip: Divide the Work; Do the Work
Establish timelines for each set of activities based on priority, time required, sequencing, etc.
Assign staff (individual or group) responsibilities for tasks
Designate lead staff for each area, responsible for assuring timeliness compliance, consistency with best practice/core concepts

## Slide 35: Refine as needed
Try it out first
Make essential changes quickly (consult with Regional Coordinator in advance).
Set review cycles to review and update:
Policies and procedures
HMIS and data
Staff job duties, training and supervision
Service delivery

## Slide 36: Key Events & Milestones
AUG | SEPT | OCT | NOV | Within 60 days of Program Implementation
One to One Calls with VA & new grantees | One to One Calls with VA & new grantees | 10/1: Agreement Effective | 11/30: All Program Operations in progress | Repository Upload
 | Post Award Conference with more in-depth training | 10/1: HMIS Set-Up |  | 
 |  | 10/1: HHS Account Set-Up |  | 

## Slide 37: Questions/Concerns/Panic Attacks
Re-review the requirements: Program Guide, VA agreement, etc.
Use the SSVF General Inbox (ssvf@va.gov)
Consult with your Mentor agency
Call your Regional Coordinator
Ask for Technical Assistance
Bring your questions to the Post Award Conference

## Slide 38: THANK YOU FOR PARTICIPATING IN THIS WEBINAR!
The presentation has been recorded and will be posted on VA’s SSVF Website:
www.va.gov/homeless/ssvf.asp