DEPARTMENT OF VETERANS AFFAIRS

RECOVERY ACT PROGRAM-SPECIFIC PLAN

VETERANS BENEFITS ADMINISTRATION

HIRING TEMPORARY CLAIMS PROCESSORS

MAY 2009

TABLE OF CONTENTS

1.  Funding Table	3

2.  Objectives	3

3.  Activities	3

4.  Characteristics	4

5.  Delivery Schedule	4

6.  Environmental Review Compliance	4

7.  Measures	4

8.  Monitoring/Evaluation	7

9.  Transparency	7

10.  Accountability	7

11.  Barriers to Effective Implementation	7

12.  Federal Infrastructure Investments	7

Appendix	8

General Operating Expenses – Claims Processors Funding Table	8

Table 1A – Account Summary	8

Table 1B – Obligations/Gross Outlays – January 2009 through December 2010 ($000)	8

1.  Funding Table

A full funding description is provided in the Appendix.

# 2.  Objectives

The American Recovery and Reinvestment Act of 2009 (ARRA or Recovery Act) provides $150 million for the hiring and training of temporary surge claims processors through 2010.  New staff will consist of approximately 500 permanent employees (who will be retained beyond 2010 to replace losses that VBA experiences as a result of normal attrition) and about 1,000 temporary employees hired under term appointments.  The temporary employees will assist in expediting disability claims development and perform other administrative activities to free decision-makers to complete more complex claims processing tasks. As a result, VBA anticipates the following improvements to projected 2010 performance: an increase in production of 10,000 cases; timeliness improvements in average days pending from 107 days down to 105 days; and average days to complete to be reduced from 154 days to 150 days.

The improved performance as a result of increased staffing corresponds with Departmental Strategic Goal 1: Restore the capability of Veterans with disabilities to the greatest extent possible, and improve the quality of their lives and that of their families.  In addition, these efforts correspond with Departmental Strategic Objective 1.2:  Provide timely and accurate decisions on disability compensation claims to improve the economic status and quality of life of service-disabled Veterans.

# 3.  Activities

Claims processing employees hired on a temporary basis will be trained at their duty stations to assist in claims processing functions, ultimately allowing fully-trained employees to focus on the core elements of claims processing.  Permanent employees will receive VBA’s existing new employee training curriculum and will be retained as other permanent employees attrite.  Supervisory training will also be given to approximately 150 existing employees who will directly supervise the new staff.

| American Recovery and Reinvestment Act Funding Administrative Costs for Temporary Surge Claims Processors * |
| --- |
| (dollars in thousands) |
|  | 2009 | 2010 | Total Obligations |
| Total FTE Levels | 385 | 1500 |  |
| Obligations |  |  |  |
| Payroll | $22,149 | $89,771 | $111,920 |
| Non-Payroll | $11,072 | $27,008 | $38,080 |
| Total Obligation | $33,221 | $116,779 | $150,000 |

*  Due to potential efficiencies gained in location of new hires and utilization of shift work,

funds originally budgeted for space may become available for hiring more temporary claims processors.

# 4.  Characteristics

There are no financial awards associated with the hiring of temporary surge claims processors.  All hiring and training will be performed in house.

# 5.  Delivery Schedule

Hiring of temporary surge claims processors begins in April 2009.  Terms for the employees who will not be retained full-time will expire in September 2010.  VBA expects to have all 1,500 FTE on board by the end of FY 2009.  A monthly hiring plan is available on VA’s Recovery web site.

# 6.  Environmental Review Compliance

Not applicable

# 7.  Measures

VBA will use three performance measures to assess the impact of ARRA funding.  Of the 3 performance measures, 2 are existing.

Measure #1

Rating-related Actions - Average Days Pending

Performance Table

| Results | Targets |
| --- | --- |
| 2006 | 2007 | 2008 | 2009 | 2010 | 2011 |
|  |  |  | Approp. | ARRA | Request | ARRA |  |
| 130 | 132 | 121 | 116 | 116 | 107 | 105 | n/a |

Other Required Information

| New or Existing Measure | Results Data Collection Frequency | Public Accessibility Modality | Results Calculation | Results Data Source | Strategic Goal Link | Strategic Objective Link |
| --- | --- | --- | --- | --- | --- | --- |
| Existing | Monthly | PAR and/or http://www.va.gov/recovery | The results are calculated by counting the number of days for all pending compensation claims that require a rating decision from the date each claim is received through the current reporting date. The total number of days is divided by the total number of pending claims | Benefits Delivery Network and VETSNET | SG 1: Restoration and Improved Quality of Life for Disabled Veterans | SO 1.2: Decisions on Disability Compensa-tion Claims |

Impact of ARRA on Performance

VA will employ approximately 1,500 claims processors with ARRA funding.   These new hires will assume responsibilities that allow trained employees to focus on the core elements of claims processing, thus speeding completion of claims determinations. The impact will be felt in FY 2010 when the amount of time that claims are pending will decline by 2 days.

Measure #2

Compensation and Pension Rating-related Actions - Average Days to Complete

Performance Table

| Results | Targets |
| --- | --- |
| 2006 | 2007 | 2008 | 2009 | 2010 | 2011 |
|  |  |  | Approp. | ARRA | Request | ARRA |  |
| 177 | 183 | 179 | 168 | 168 | 154 | 150 | n/a |

Other Required Information

| New or Existing Measure | Results Data Collection Frequency | Public Accessibility Modality | Results Calculation | Results Data Source | Strategic Goal Link | Strategic Objective Link |
| --- | --- | --- | --- | --- | --- | --- |
| Existing | Monthly | PAR and/or http://www.va.gov/recovery | The average elapsed time (in days) it takes to complete compensation and pension claims that require a rating decision is measured from the date the claim is received by VA to the date the decision is completed | Benefits Delivery Network and VETSNET | SG 1: Restoration and Improved Quality of Life for Disabled Veterans | SO 1.2: Decisions on Disability Compensa-tion Claims |

Impact of ARRA on Performance

VA will employ approximately 1,500 claims processors with ARRA funding.  These new hires will assume responsibilities that allow trained employees to focus on the core elements of claims processing, thus speeding completion of claims determinations.  The impact will be felt in FY 2010 when claims processing time will decline by 4 days.

Measure #3

The number of ARRA-funded claims processors hired

Performance Table

| Results | Targets |
| --- | --- |
| 2006 | 2007 | 2008 | 2009 | 2010 | 2011 |
|  |  |  | Approp. | ARRA | Request | ARRA |  |
| n/a | n/a | n/a | n/a | 1,500 | n/a | n/a | n/a |

Other Required Information

| New or Existing Measure | Results Data Collection Frequency | Public Accessibility Modality | Results Calculation | Results Data Source | Strategic Goal Link | Strategic Objective Link |
| --- | --- | --- | --- | --- | --- | --- |
| New | Monthly | PAR and/or http://www.va.gov/recovery | The number of ARRA-funded employees hired | PAID | SG 1: Restoration and Improved Quality of Life for Disabled Veterans | SO 1.2: Decisions on Disability Compensa-tion Claims |

Impact of ARRA on Performance

VA will employ approximately 1,500 claims processors with ARRA funding.   VA will complete this hiring by 30-September 2009.  Positive performance impacts will be felt in FY 2010.

# 8.  Monitoring/Evaluation

VBA operations reports will provide data on the average days to complete claims and production volume for work performed by the temporary surge claims processors.  Reports will be run monthly.  Staffing increases will be tracked via bi-weekly pay period reports.

# 9.  Transparency

There will be updates to VA’s Recovery web site for information relating to temporary surge claims processors hired.

# 10.  Accountability

VBA has set hiring goals for the temporary surge claims processors which will be monitored via bi-weekly pay period reports. If Regional Office (RO) Directors are unable to meet hiring goals by the end of August, it may be reflected in their performance evaluation.  If current claims processors are temporarily promoted to supervise the new hires, their new supervisory duties may be incorporated into their performance evaluations.

# 11.  Barriers to Effective Implementation

There are no anticipated barriers to hiring the temporary surge claims processors.

# 12.  Federal Infrastructure Investments

Not applicable

# Appendix

## General Operating Expenses – Claims Processors Funding Table

## Table 1A – Account Summary

|  | TAFS (pick from dropdown) | Appropriated to TAFS ($000s) | Program Allocations |
| --- | --- | --- | --- |
|  |  |  | BA Allocation ($000s) | Program Name |
| One account funding one program | (36-0150 2009 \ 2011) General Operating Expenses | 150,000 | 150,000 | GOE Recovery Act |

## Table 1B – Obligations/Gross Outlays – January 2009 through December 2010 ($000)

| Funding Type | Funding Year |  |
| --- | --- | --- |
| Obligation | 2009 | $33,221 |
| Gross Outlay | 2009 | $31,560 |
| Obligation | 2010 | $116,779 |
| Gross Outlay | 2010 | $118,440 |